## Trang tính1
Capstone JS
STT | Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
1 | index.html |  |  |  | Chí Cường
2 | register.html |  |  |  | Loan Trần
3 | detail.html |  |  |  | Loan Trần
4 | API |  |  |  | Chí Cường
5 |  |  |  |  | Loan Trần
| link Figma | https://www.figma.com/file/pBNckNoXdG7Oz2Al8KecmF/Capstone-project-cybersoft---design-by-Tr%C6%B0%C6%A1ng-T%E1%BA%A5n-Kh%E1%BA%A3i?node-id=24%3A260
| link API tổng hợp | https://shop.cyberlearn.vn/swagger/index.html

## Trang tính2
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Header | 2020-12-10 | 12/13 | 100% | Dev1 |  | 2020-12-14 | 95% | Dev2
Logo |  |  | 50% | Dev A |  | 2020-12-14 | 50% | Nhật Trường
Navbar | 2019-05-23 | 2019-07-01 | 90% | Dev A |  | 2020-12-14 | 90% | Nhật Trường
Submenu | 2019-05-23 | 2019-05-31 | 100% | Dev A |  | 2020-12-14 | 100% | Nhật Trường
Search form | 2019-06-20 | 2019-06-28 | 90% | Dev A |  | 2020-12-14 | 90% | Nhật Trường
Login popup | 2019-06-25 | 2019-07-01 | 80% | Dev A |  | 2020-12-14 | 80% | Nhật Trường
Carousel | 2020-12-10 | 2020-12-13 | 100% | Dev1 |  | 2020-12-14 | 100% | Dev2